## PCO Register
PCO # | Contract charged (proposed) | Confirm? | Vendor | AP PO # | Vendor quote / ref | Lot / tender pkg | Scope | Amount CAD (pre-tax) | Amount basis | Kylie approval | Status / open issue | Source email (date)
PCO-001 | eStruxture direct account | Y | Texcan | 2766-CAL3-0002 (rev) | Q-1018940 / OA 1750503 | GENERAL STOCK (DHA/DHE) | 751 m MV105 1C-750 35kV Cu EPR cable. Trevor: general stock, to be pulled for DHA/DHE in new year. Factory price adjustment to $211.44/m. | 158791.44 | AP PO 2766 rev + Texcan OA 1750503 (tax 7,939.57 extra) | Original approved 2026-10-05; revised PO awaiting Kylie | Future-phase stock, not Phase 1 Package B scope. Prysmian stock lengths 178/187/189/197 m, 2 wk delivery, +/-5% tolerance, price subject to tariff at shipment. | 2026-10-20
PCO-002 | eStruxture direct account | Y | Magna IV Engineering | not yet issued | Q-188471 | TP-DHC-01I (Nishi) / DH-D per Devon | CAL-3 Phase 2 DHD MV terminations & testing, lump sum. Same scope as DHC. OEM lead times do not meet schedule; alternates offered. | 119500 | Magna Q-188471 lump sum, excl. tax; extras at $135/hr blended | Conditional (Kylie 2026-10-13): lead-time alternates must be confirmed | Devon told Keith to proceed 2026-10-13. Nishi re-requested approval 2026-10-20 under TP-DHC-01I. PO not yet issued. Phase 2 scope: confirm whether this is a Package B change or owner-direct. | 2026-10-13 / 2026-10-20
PCO-003 | AP Package B site work (PO6246) | Y | Magna IV Engineering | 2924-CAL3-0002 | Q-176183 | CAM-TMP-01 | CAL-3 temp power MV terminations & testing (June 2026 work). Original quote, PO issued 2026-10-20 after work done. | 18950 | AP PO 2924 (matches Q-176183 total) | Trevor approved quote 2026-06-13; PO issued 2026-10-20 | Work done June 2026 without PO. Temp power responsibility (AP vs owner) to confirm. | 2026-10-20
PCO-004 | AP Package B site work (PO6246) | Y | Magna IV Engineering | 2924-CAL3-0002 (not on PO) | CO #001 A5344-310776 | CAM-TMP-01 | Change order: 126 hrs additional labour/OT/DT ($17,010) + material ($3,122.34) for temp power setup. Cable type change, delays, extra Vista switch parts and termination kits. | 20132.34 | Magna CO #001 dated 2026-09-01 | Not approved. Keith asked 2026-10-20 whether CO can be invoiced | PO 2924 covers $18,950 only. CO not on PO. Decision needed: approve/reject CO and who carries it. | 2026-10-20
PCO-005 | AP Package B site work (PO6246) | Y | Trinity Power (Sunbelt Solomon) | 2812-CAL3-0002 | RA 105124 R2 (Oct) / 105267 (Nov) | none on PO (Kylie asked for work package no.) | Rental 6 x Avtron 720 kW liquid-cooled load banks + 3000A 600V dist, 6 x 800A breakers, cam cables, SPE-1000 cert, delivery and return freight. 28-day rental, Oct requirement. Nov order (7 units) separate RA. | 172310 | AP PO 2812 total | Signed by Joey/Angelo 2026-10-14; Kylie approval requested 2026-10-15; PO sent 2026-10-15 | Kolostat (Adrien) confirms it is AP's PO. Kylie: needs a work package number so AP can invoice it. Nov RA 105267 not on this PO. Freight 14,319 + 12,519 return. | 2026-10-15
PCO-006 | AP Package B site work (PO6246) | Y | Sunbelt Rentals | 2866-CAL3-0002 | Q-80525227 Rev 2 | TP-DHC-01H COMMISSIONING | Rental 1 x 1250 kW 480 V resistive load bank + 48 x 50 ft cam cables + 16 pigtails, 4-week rate, 3rd-party freight delivery and return. | 15729 | AP PO 2866 total | Approved; PO sent 2026-10-16 | Freight renegotiated (Nishi: cannot pay over $16k freight). UPS testing. | 2026-10-16
PCO-007 | AP Package B site work (PO6246) | Y | Sunbelt Rentals | 2791 | Contract 80519077 | none | Temp cooling: 2 x 5T portable AC, 400A cam distro, fan, duct, spider box cables, E&D labour, 4 weeks (Oct 14 to Nov 11). Two additional 5T units requested 2026-10-13 on new PO. | 9687.55 | Sunbelt reservation 80519077 subtotal (GST 484.39 extra) | Approved 2026-10-15 | Second PO for 2 additional units not yet seen in folder. | 2026-10-15
PCO-008 | AP Package B site work (PO6246) | Y | JM Test Systems (BHD) | 2915-CAL3-0002 | RQ24624 | TP-DHC-1H | Rental Fluke 1777 power quality analyzer + 3 x 6000A flex CTs, 28-day rate Oct 19 to Nov 15. Marty expects 3 months. | 2295 | AP PO 2915 / RQ24624 (28 days only) | Approved; PO sent 2026-10-19 | JM Test wants credit card; Nishi asking for account terms. 3-month need = ~3x this amount. | 2026-10-19
PCO-009 | AP Package B site work (PO6246) | Y | Crystal Services | 2885-CAL3-0002 | Invoice 9812 | none | Equipment moves Sept 28 to Oct 2: switchgear hoist to level 2 by zoom boom, generator jack/level, exhaust piping removal, switchgear unload at warehouse. Sterling+operator, supervisor, labourers, zoom boom rental. | 29100 | Invoice 9812 subtotal (GST 1,455 extra); PO 2885 matches | Approved by Kylie 2026-10-15; PO sent 2026-10-16 | OFCI equipment handling. Candidate for DA2 OFCI coordination line if owner agrees; otherwise Package B. | 2026-10-16
PCO-010 | AP Package B site work (PO6246) | Y | Rodeo Cutting & Coring | not yet issued | Inv 58340, 57846, 57847, 58299 | none | Scanning, coring, handsawing Sept 7 to Oct 3 (electrical rooms, precast walls, exterior holes, lobby slab). | 21852.5 | Sum of 4 invoice subtotals (8,060 + 300 + 8,330 + 5,162.50); GST extra; totals incl. GST 22,945.15 | Requested 2026-10-19; Ryan confirmed work complete | Four invoices with no PO. Base-building penetrations: confirm AP vs GC responsibility. | 2026-10-19
PCO-011 | AP Package B site work (PO6246) | Y | Phoenix Energy Services | not yet issued | Invoice PSI-73097 | SITE WORK | T&M labour Oct 5 to 11 with signed tickets. Edward confirmed hours match timecards (truck and 3rd-party charges not tracked by AP). |  | Invoice PDF is scanned; amount not extractable here | Requested 2026-10-15 and 2026-10-16 | Amount to be read from invoice. T&M authorization lines were blank per earlier review. | 2026-10-16
PCO-012 | AP Package B site work (PO6246) | N | Unitray Systems | 2822-CAL3-0002 rev 3 | QT006732-1 | TP-CSB-04R | Cable tray, fittings, rubber roof supports (30 x 457 mm, 20 x 244 mm), freight. Heat trace, fire alarm and exhaust fan access. | 14767.11 | AP PO 2822 rev 3 | Approved 2026-10-14 (rev 3 lower than prior) | Shipped to warehouse. | 2026-10-14
PCO-013 | eStruxture direct account | Y | Solution Control Systems | 2271-CAL3-002 / 2273-CAL3-0002 / CAL3-SCS26-2095 / CAL3-SCS26-2038 | Jonny Lee email 2026-07-22 | GEN LB camlock / UPS busducts | Camlocks sourced via US; cost impact $22k to $25k plus shipping and tariffs (SCS). Separate: battery cabinet covers crate to Edmonton for ground-bus modification, freight liability unresolved. | 22000 | SCS estimate low end ($22k to $25k), not quoted | No approval on record | OFCI vendor scope change. Who pays camlock premium and cover freight is open. CAL3-SCS26 numbers look like owner POs: confirm contract. | 2026-10-20
PCO-014 | AP Package B site work (PO6246) | N | Anixter / Wesco | pending | Q00HQ9GG | MR-TP-DHC-1E | 768 m 600 kcmil Cu RW90 + 900 m #2 Cu RW90 green. Alberta stock. | 77485.2 | Anixter quote total | Approved 2026-10-19 | Price valid 5 days, metal escalation. Flat deck freight extra. | 2026-10-19
PCO-015 | AP Package B site work (PO6246) | N | Texcan | pending | Q-1021418 | TP-DHC-01A | 450 m RW90 250 MCM Cu (MR asked 400 m). Calgary stock. | 16776 | Texcan quote (450 m x $37.28) | Approved 2026-10-20 | 450 vs 400 m not resolved; metal adjustment at shipment. | 2026-10-20
PCO-016 | AP Package B site work (PO6246) | N | Noramco | pending | Q-1600617 | TP-DHC-04 | 94 m 250 MCM Cu RW90 (30 m + 64 m). Only supplier with stock. | 3815.46 | Noramco quote | Approved 2026-10-16 |  | 2026-10-16
PCO-017 | AP Package B site work (PO6246) | N | Gescan | pending | 18240937-00 | TP-CSB-02B | Wiremold floor box parts for NOC room missed box + $200 expedite freight. | 1153.05 | Gescan quote incl. freight | Requested 2026-10-16 | 7 to 15 working days from Wiremold. | 2026-10-16
PCO-018 | AP Package B site work (PO6246) | N | Gescan | pending | 18247665-00 | TP-CSB-09 | 15 x 4 in square covers (30 requested, 15 in stock). | 459.92 | Gescan quote (30 pcs); 15 pcs = 229.96 | Requested 2026-10-16 |  | 2026-10-16
PCO-019 | AP Package B site work (PO6246) | N | Graybar | pending | 516513-00 rev | TP-DHC-03B | 150 x T&B universal clamps (tray down), air freight from Quebec. 350 requested. | 868 | Graybar quote: 828 + 40 freight (GST 43.40 extra) | Approved 2026-10-20 | Remaining 200 to be sourced elsewhere. | 2026-10-20

## Lot materials (Pkg B)
Vendor | Quote / bid | Lot / tender pkg | Note from thread | Kylie approval | Date | Amount
EWCL | S1813982 / S1813988 / S1814008 | various | Jeff Bosch chasing approval | Pending | 2026-10-20 | in bid PDF
EWCL | S1814255 | TP-DHC-1A | wire, 2 to 3 day ETA | Pending | 2026-10-19 | in bid PDF
EWCL | S1814232 | TP-CSB-09B | in-stock items only | Pending | 2026-10-19 | in bid PDF
EWCL | S1814203 | TP-CSB-09 | in-stock items only | Pending | 2026-10-19 | in bid PDF
EECOL | Q-956984 | TP-DHC-02A | stocked, pickup same day | Pending | 2026-10-20 | in quote PDF
EECOL | Q-954829 | CAM-TMP-01 | spider box, in stock | Pending | 2026-10-19 | in quote PDF
EWCL | S1813895 / S1813896 | TP-CSB-05A / TP-DHC-05A | all in stock; acknowledged, ships Monday | Approved 2026-10-15 | 2026-10-15 | in bid PDF
EWCL | S1813292 / S1813295 / S1813302 | GENERAL STOCK | in stock + under 1 week; MR revised | Requested 2026-10-16 | 2026-10-16 | in bid PDF
EWCL | S1813595 | CAM-TMP-01 | in-stock only; HAL UHBS2 substituted for RENO HBU | Requested 2026-10-16 | 2026-10-16 | in bid PDF
EECOL | Q-2997666 | TP-DHC-08A | stocked | Approved 2026-10-16 | 2026-10-16 | in quote PDF
EECOL | Q-951766 | TP-DHC-03B | 1 item in stock | Approved 2026-10-16 | 2026-10-16 | in quote PDF
Amazon | n/a | TP-DHC-01B | rubber edge, short 2000; 30 pcs 50 ft | Requested 2026-10-16 | 2026-10-16 | n/a
EECOL | 955640 | TP-CSB-04R | all in stock | Approved 2026-10-15 | 2026-10-15 | in quote PDF
EECOL | Q-299786 | TP-DHC-08C | in stock | Approved 2026-10-15 | 2026-10-15 | in quote PDF
City Electric | NEC/053215 | TP-DHC-02A | in stock | Approved 2026-10-15 | 2026-10-15 | in quote PDF
EECOL | Q-955980 | TP-CSB-09 | all in stock | Approved 2026-10-15 | 2026-10-15 | in quote PDF
EECOL | Q-956063 | TP-DHC-01C | 3 items | Approved 2026-10-15 | 2026-10-15 | in quote PDF
Texcan | Q-1020827 | TP-DHC-01C | stock, weekend work | Approved 2026-10-15 | 2026-10-15 | in quote PDF
Bolt Supply | 9482309-00 | TP-DHC-01C | all non-electrical items | Approved 2026-10-15 (after call) | 2026-10-15 | in quote PDF
EWCL | S1813928 | DHC 2A | in-stock items; 2 not stocked | Pending | 2026-10-15 | in bid PDF
EWCL | S1813874 | TP-CSB-02A | 4 week ETA | Pending | 2026-10-15 | in bid PDF
EWCL | S1813894 | TP-CSB-09 | PVC boxes declined | Declined | 2026-10-15 | n/a
EWCL | S1813893 | TP-DHC-02A | in stock | Pending | 2026-10-15 | in bid PDF
EWCL | S1813825 | TP-DHD-01B | multiple options | Pending | 2026-10-15 | in bid PDF
EWCL | S1812850 | TP-CDB-09 | blue liquid tight; pre-approved by Angelo | Approved 2026-10-15 | 2026-10-15 | in bid PDF
EBH | Q-11338521 | TP-CSB-09 | basket tray covers, only supplier before month end | Requested 2026-10-14 | 2026-10-14 | in quote PDF
Amazon | n/a | TP-CSB-02F | Brady lockbox LOTO | Approved 2026-10-14 | 2026-10-14 | n/a
EWCL | S1813542 | TP-DHC-02A | in stock; ships Friday | Approved 2026-10-14 | 2026-10-14 | in bid PDF
City Electric | NEC/053203 | TP-DHC-01E | 30 m in stock | Approved 2026-10-14 | 2026-10-14 | in quote PDF
City Electric | NEC/053208 | TP-DHC-01A | 2 items | Approved 2026-10-14 | 2026-10-14 | in quote PDF
City Electric | NEC 053143 | TP-DHC-02B | all in stock | Approved 2026-10-14 | 2026-10-14 | in quote PDF
EWCL | S1812899 | TP-CSB-04R | in-stock items; 10 KO fillers sold out | Approved 2026-10-14 | 2026-10-14 | in bid PDF
EWCL | S1813747 | TP-DHC-01C | 1 week ETA items only | Pending | 2026-10-14 | in bid PDF
EWCL | S1812912 | TP-DHC-08A | slotted shipped in error; RMA, solid in stock | n/a (RMA) | 2026-10-14 | n/a
EWCL | S1813609 | TP-DHD-01A | 4 options | Pending | 2026-10-14 | in bid PDF
EECOL | Q-955351 | n/a | motion sensor switch (Devon) | Approved 2026-10-14 | 2026-10-14 | in quote PDF
Alberta Breaker | Q-29225 / Q-29227 | TP-DHC-01E | 18 in stock + 100 air freight | Approved 2026-10-14 | 2026-10-14 | in quote PDF
EWCL | S1813601 | DHC-01F | in-stock items | Approved 2026-10-14 | 2026-10-14 | in bid PDF
EWCL | S1813305 | TP-DHC-01E | 20 pcs in stock | Approved 2026-10-14 | 2026-10-14 | in bid PDF
EWCL | S1813568 | TP-DHD-1E | in-stock items | Approved 2026-10-14 | 2026-10-14 | in bid PDF
EWCL | S1813502 | TP-CSB-05A | in-stock items | Approved 2026-10-14 | 2026-10-14 | in bid PDF
Amazon | n/a | TP-DHC-01B | rubber edge, $60/roll vs EECOL $500/roll | Approved 2026-10-14 | 2026-10-14 | n/a
EECOL | Q-2425750 | TP-CSB-02B | extra exit signs, Joey pre-approved | Approved 2026-10-14 | 2026-10-14 | in quote PDF
EWCL | S1813346 | TP-DHC-1F | all items incl. short lead | Approved 2026-10-14 | 2026-10-14 | in bid PDF
EWCL | S1813332 | TP-DHC-01E | in stock + MR qty 20 line 2 | Approved 2026-10-14 | 2026-10-14 | in bid PDF
EWCL | S1813360 | TP-DHC 2A | in-stock items | Approved 2026-10-14 | 2026-10-14 | in bid PDF
EWCL | S1813351 | CAM-TMP-01 | all in stock | Approved 2026-10-14 | 2026-10-14 | in bid PDF
Uline | n/a | TP-CSB-05A | only stocked at Uline | Requested 2026-10-14 | 2026-10-14 | n/a
CES (City Electric) | NEC053193 | TP-CSB-09 | 2 items | Approved 2026-10-13 | 2026-10-13 | in quote PDF
City Electric | NEC53172 | TP-DHC-01D | 4 items in stock | Approved 2026-10-13 | 2026-10-13 | in quote PDF
EWCL | S1813349 | TP-DHC-1E | 60 m or 45 m options, 2 to 6 wk | Pending | 2026-10-13 | in bid PDF
EWCL | S1813370 | TP-CSB-05A | 3 options | Pending | 2026-10-13 | in bid PDF
Bolt Supply | 9477946-00 / 9470948-00 / 9471032-00 | GENERAL STOCK | bulk order, Allan; PO done, OA received, no ETA | Approved (prior) | 2026-10-13 | in quote PDF
EECOL | Q-954899 | TP-DHC-01B | rubber edge; Kylie flagged $500/roll vs Amazon $60 | Challenged | 2026-10-13 | in quote PDF
EBH | Q11347666 | TP-DHC-05A | 1 item | Approved 2026-10-13 | 2026-10-13 | in quote PDF
Bolt Supply | 9482312-00 | TP-CSB-09 | in stock | Approved 2026-10-13 | 2026-10-13 | in quote PDF
City Electric | NEC53170 | TP-DHC-02A | see Kylie note | Approved 2026-10-13 | 2026-10-13 | in quote PDF
Gescan | 18221956-00 | TP-DHC-01E | 14 x #6 lugs | Approved 2026-10-06 | 2026-10-06 | in quote PDF
Westburn / Burndy | LUGS.xlsx list | various | LLSCO lug shortage, 22+ wk leads; air freight option | Open | 2026-10-20 | n/a

## Contracts
Contract | Parties | Value CAD | Source
Package B PO6246 (electrical subcontract, supplemental conditions) | Leeswood Construction / AP Electric (CGL) | 72260828.62 | SoV memo 2026-08-27 (Attachment R4)
DA2 / OFCI Coordination Services Agreement | eStruxture / CGL Inc. direct | 2739171.38 | SoV memo 2026-08-27 (Attachment R3)
eStruxture direct accounts | eStruxture / vendor |  | Owner-direct purchases (future phase stock, OFCI vendor changes)

## Totals
Contract charged (proposed) | Count | Amount CAD (pre-tax, items with amounts)
eStruxture direct account | 3 | 300291.44
AP Package B site work (PO6246) | 16 | 405381.13